## Sheet1
| Pre-Project Period | Project Matching | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10
Group Source (GS) |  | Project Matching: Coordinating both PPD and PPFfor matching | Weekly Check in: Small questionairre for both PL and PM | Weekly Check in: | Weekly Check in |  | Bi-Weekly Check: Transition to Bi-weekly from weekly |  | Bi-Weekly Check |  | Bi-Weekly Check | Deliverables Week
|  | Curriculum Development: Initially whole GS team works with each PL for curriculum/10 week plan, then transition to 1 GS memb per PL, than supervisory structure | Week 1: Small questionairre for both PL and PM; Week 10: Helping develop presentation of deliverables
|  |  |  | Goals Skills Check: Check in with students about LG |  | Goals Skills Check |  | Goals Skills Check |  | Goals Skills Check |  | Final Check in in Goals (Longer Questionaire)
Feedback
Based on Feedback adapt program, working with mentors to alter "curriculum" help better achieve student LGs and achieve Project Goals
Project Lead (PL) | Project Paramter Definition (PPD)
Respond to Questions
Establish clear LG or Curriculum
Skills from Membs
Project: Collaborative Working and Individual Working
Project Members (PM) | Project Preference Form (PPF)
| Respond to Questions |  | Week 10: Presentation of Deliverables
Desired LG
Desired Skills
To do: | Defining Goal Skills Check | Defining per week, how each check will work, what they will be measuring (quantitative vs qualitative data) | Week 1: Laurel
| Defining Weekly Check Ins |  | Week 1: Leo
| Deliverables (facilitation) | James | Week 1: James
| Ideas: | Journaling the achievement of goals (self-aware of learning) and building to writing more about experience in resumé and cover letter